## CM Constraints
Time |  | Cost |  | Quality
| Private |  | Traditional |  | Straightforward
Sector Type - | PPP | Procurement Method - Precise | Design & Build | Technical Complexity - Limited | Difficult
| Public |  | Other |  | Complex
| Slightly Restricted |  | US$ 0 - 1 million |  | Little Influence
Site Logistics - | Restricted | Project Budget- | US$ 1 - 5 million | Stakeholder Involvement - Large Involvement | Influencial
| Severely Restricted |  | US$ 5 + million |  | Very Influencial
| 0 - 1 Year |  | Minimum |  | Balanced
Project Duration- | 1 - 2 Years | Resource Control - High Level Needed | Measured | Carbon Footprint - | Benchmark
| 2 + Years |  | Total |  | Carbon Credits Used
CM Constraints based on Specific Project
Sector Type - | Public | Procurement Method - Precise | Design & Build | Technical Complexity - | Straightforward
Site Logistics - | Restricted | Project Budget- High Importance | US$ 5 + million | Stakeholder Involvement - | Very Influential
Project Duration - | 2 Years | Resource Control - High Level Needed | Total | Carbon Footprint - | Benchmark

## Eg. Project Constraints
Example of Project Specific Constraints based on (study) Dublin (IRE) Local Authority BIM Project | Successful CM Criteria based on 'iron triangle' | Attributes Based on Constraints | 4D BIM Application Selection Criteria based on Lit Review | Planned Outputs
| Time |  | Mangement
Sector Type - Public |  | Simulation |  | Data management
Site logistics - Restricted |  | Discreet event simulation |  | Risk management
Project Duration- 2 Years |  | Schedule vs actual (WIP) |  | Asset management
| Cost |  | Value
Procurement Method - Design & Build |  | Data control |  | Earned value
Project Budget- High Importance |  | Quantity Take Off |  | Cost control
Resource Control - Total |  | Animations |  | Resource management
| Quality |  | Technical
Technical Complexity - Straightforward |  | Quality control |  | Quality assurance
Stakeholder involvement - Very Influencial |  | Interoperability |  | Collaboration
Carbon Footprint - Benchmark |  | Clash detection |  | Visualisation

## Attributes based on Constraints
Attributes Based on Constraints
Project Title: |  | Scores for Project Based Software Application Atributes Between 0 - 10
Project Location: | Schedule vs actual (WIP)
Country: | Discreet event simulation
City: | Simulation
Local Authority: | Quantity Take Off
Individual Project Involvement: | Data control
Date of Project: | Animations
4D Software Application Used: | Quality control
Software Application Version: | Interoperability
Clash detection
Aggregate Score